## 3. Stories
Story# | Story | Dev Pts | QE Pts | Total Pts | Commit | Stretch | Status | PO Reviewed
1 | Infra Setup- Connectivity, Development Environment | 0.2 | 0 | 0.2 | Y |  | Completed | Yes
2 | UX Design - Mockups (Figma) | 0.5 | 0 | 0.5 | Y |  | Completed | Yes
3 | AAOS application development-Develop AAOS application using car library to display car speed | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
4 | AAOS application development- Get car speed limit on starting the application | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
5 | AAOS application development-Monitor car speed & report speed if it exceeds speed limit | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
6 | IOS Application Screen-1: Enter Vehicle number. Display this screen if vehicle number is not present. Skip this screen if vehicle number already entered before. This simulates login. | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
7 | IOS Application: Screen-2: Display vehicle number. Fetch the speed limit from backend for the given vehicle number. Allow user to set speed limit and submit the new speed limit to backend. | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
8 | IOS Application : Screen-3: Fetch speed violation data from the backend and display in Map view. Plot the location markers on the map. Click on the marker to display speed, date & time. | 1 | 0.2 | 1.2 | Y |  | In-Progress | No
9 | Android Application- Screen-1: Enter Vehicle number. Display this screen if vehicle number is not present. Skip this screen if vehicle number already entered before. This simulates login. | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
10 | Android Application: Screen-2: Display vehicle number. Fetch the speed limit from backend for the given vehicle number. Allow user to set speed limit and submit the new speed limit to backend. | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
11 | Android Application : Screen-3: Fetch speed violation data from the backend and display in Map view. Plot the location markers on the map. Click on the marker to display speed, date & time. | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
12 | Backend - Database Setup & Design - Schema, Table & Data Creation | 1 | 0 | 1 | Y |  | Completed | Yes
13 | Backend - API Development - Create an API which sets the speed threshold for the given VIN | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
14 | Backend - API Development - Create an API which displays the speed threshold set for the given VIN | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
15 | Backend - API Development - Create an API which captures the speed violation report for the given VIN, capture the dataset (Violation Date & Co-ordinates) | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
16 | Backend - API Development - Create an API which lists the number of violation reported for the given VIN | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
17 | Backend - API Development - Create an API which deletes all the violations reported for the given VIN | 1 | 0.2 | 1.2 | Y |  | Completed | Yes
18 | Backend - API Deployment | 0.5 | 0 | 0.5 | Y |  | Completed | Yes
19 | Deployment in AWS | 0.5 | 0 | 0.5 |  | Y | In-Progress | No
20 | Implement automatization in CI/CD | 0.5 | 0.2 | 0.7 |  | Y | Not Assigned | No
21 | Integration of Monitoring (Dynatrace, Splunk ) | 0.5 | 0.2 | 0.7 |  | Y | Not Assigned | No
22 | Documentation | 0.5 | 0 | 0.5 |  | Y | In-Progress | No

## 4. Team Capacity
Team Name: |  | SKODA_POC
Scrum Team |  | Poonam, Rakesh, Suresh, Bharanitharan, Hari
Product Owner |  | Mehul
Scrum Master |  | Soham
Team Size : |  | 5
Total Capacity : Working Days |  | 21
Focus Factor |  | 90%
Story Points - Planned |  | Commited - 19 | Stretch - 2.4
Capacity | Member 1 - Lead | Member 2 - Android Engineer | Member 3 - IOS Engineer | Member 4 - Backend Engineer | Member 5 - UX Engineer
Day 1 | 1 | 1 | 1 | 1 | 1
Day 2 | 1 | 1 | 1 | 1
Day 3 | 1 | 1 | 1 | 1
Day 4 | 1 | 1 | 1 | 1
Day 5 | 1 | 1 | 1 | 1
Total | 5 | 5 | 5 | 5 | 1

## 5. API Spec
S.No | API | Operation | Request | Response | Remarks
1 | http://localhost:8090/setSpeedThreshold | POST | { "vin": "veh2", "speedLimit": 95 } | { "vin": "veh2", "speedLimit": 95 } | Performs both insert and update, if VIN is already exist in DB
2 | http://localhost:8090/getSpeedThreshold/veh2 | GET |  | If VIN number is found, reponse: { "vin": "veh2", "speedLimit": 95 } If VIN not found,response: { "vin": "No Record Found for given VIN veh20", "speedLimit": 0 }
3 | http://localhost:8090/reportSpeedViolation | POST | { "vin": "veh2", "speedLimit": 95, "violatedDate":"2024-10-20 10:00:00", "latitude":100.00, "lalangitude":-125.63 } | { "vin": "veh2", "speedLimit": 95, "violatedDate": "2024-10-19 22:30:00", "latitude": 100.0, "langitude": -125.63 } | This api accepts multiple records for the same vin
4 | http://localhost:8090/getSpeedViolation/veh1 | GET |  | [ { "id": 1, "vin": "veh1", "speed_limit": 95, "violatedDate": "2024-10-19 22:30:00", "latitude": 100.0, "langitude": -125.63 }, { "id": 2, "vin": "veh1", "speed_limit": 95, "violatedDate": "2024-10-19 10:30:00", "latitude": 100.0, "langitude": -125.63 } ] | if no record found, response will be null object.

## 6. DB Spec
| Table | Vehicles | [5 empty] | Table | Vehicle_Violations
| Column | Primary Key | Type | Length | Sample Value |  |  | Column | Foreign Key | Type | Length | Sample Value
| VIN | Y | Text | 10 | mh12em1234 |  |  | VIN | Y | Text | 10 | mh12em1234
| SpeedLimit | N | Text | 3 | 40 |  |  | violoatedSpeedLimit | N | Text | 3 | 40
[8 empty] | Date |  | Timestamp |  | 2024-10-22 10:30
[8 empty] | Lattitude |  | Text/Float
[8 empty] | Langitude |  | Text/Float
[8 empty] | UID | Primary Key |  |  | use this if JPA throws any error otherwise not needed
Table | Vehicle | [5 empty] | Table | Vehicle_Violation
VIN | SpeedLimit |  |  |  |  | UID | VIN | violoatedSpeedLimit | Date | Lat | Long
mh12em1234 | 50 |  |  |  |  | abcd-efg-1 | mh12em1234 | 80 | 2024-10-21 08:00 | 10 | 20
mh12em1235 | 50 | [5 empty] | mh12em1234 | 70 | 2024-10-11 10:00 | 50 | 60
mh12em1236 | 50 | [5 empty] | mh12em1234 | 75
mh12em1237 | 50 | [5 empty] | mh12em1234 | 50
mh12em1238 | 50 | [5 empty] | mh12em1234 | 50
mh12em1239 | 50 | [5 empty] | mh12em1235 | 80
mh12em1240 | 50 | [5 empty] | mh12em1235 | 80
mh12em1241 | 50 | [5 empty] | mh12em1235 | 80
mh12em1242 | 50 | [5 empty] | mh12em1235 | 80
mh12em1243 | 50 | [5 empty] | mh12em1235 | 80
mh12em1244 | 50 | [5 empty] | mh12em1235 | 80
mh12em1245 | 50 | [5 empty] | mh12em1235 | 80

## 8. Burndown Chart
Time |  | Open Story Points
Day | Date | Planned (SP) | Remaning (SP)
0 | ## | 19 | 19
1 | 2024-10-21 | 15 | 17
2 | 2024-10-22 | 11 | 13
3 | 2024-10-23 | 7 | 9
4 | 2024-10-24 | 4 | 4.8
5 | 2024-10-25 | 0 | 1.2
Sprint | Committed (SP) | Stretched (SP) | Achieved (SP) | Achieved %
1 | 19 | 2.4 | 17.8 | 93.68%